**Scope of work**

|  |  |  |
| --- | --- | --- |
| **Timeline** | **Activity** | **Milestone** |
| September 2021 | * Review Fintech profiles/partners in India * Cold calling new potential partners in telecom, insurance, healthcare, government stakeholders and tech companies offering tech apps such as e-vouchers and mobile wallets * Host F4H\_SIG\_Launch Session 1 - **September 29, 2021** | * Final list of partners with potential to scale and/or integrate with other partners for co-creating common products * SIG Session 1\_Launch Report |
| October 2021 | * Host SIG Session 2 – “Align NDHM to support scaling eRUPI through better integrated service solutions” – **October 15, 2021** | * Finalize 1-2 partners to scale Arogya Finance * SIG Session 2 Report |
| November 2021 | * Host SIG Session 3 – “Health Wallets with integrated service solutions” – November 8, 2021 | * List of potential partners for integrated Health Wallet * SIG Session 3 Report |
| December 2021 | * Carry forward discussion with identified health tech and Fintech partners to collaborate and support development of comprehensive health wallet | * Finalize 1-2 partners to integrate as a comprehensive Health Wallet |

To create a platform for knowledge sharing and dialogue between Fintech and Health-tech players, in order to create new partnerships/models supporting health financing for the lower income segment.

**Compensation**

A fee of USD 3,000 per month will be paid to the Consultant. The Consultant will be working 15 days a month. The payment will be released only on the completion of deliverables and invoicing by the Consultant.

**Term**

This engagement shall commence upon execution of this Agreement. The Agreement shall continue in full force and is effect from **September 1, 2021** to **December 31, 2021**.