**Scope of Work**

**Fintech for Health for year 3**

1. **Support Existing Project of Yibao and Alipay:**
   * Provide continued technical support to Yibao for the expansion of product solutions and uptake in line with MOU/partnership agreement, and with soliciting and documenting population-reach impact metrics from partners every month (e.g., # of people who have access, # of people who availed, # of people reached)

Cost: USD 20,000

* + Continue to develop Alipay project and uptake in line with MOU/partnership agreement. Solicit and document population-reach impact metrics from partners every month (e.g., # of people who have access, # of people who availed, # of people reached). Launch the project by the end of 2021 with a potential impact number of 50,000 ppl by March 2022.

Cost: USD 10,000

1. Administrative cost and overhead: USD 5,000

**Service Fee**

The total service fee for this engagement is USD 35,000.

**Payment Schedule**

|  |  |
| --- | --- |
| Upfront mobilization | 20,000 |
| Launch of Alipay project | 10,000 |
| Continued support for Yibao and Alipay (July 30, 2022) | 5,000 |
| **Total** | **USD 35,000** |

**Term**

This engagement shall commence upon execution of this Agreement. The Agreement shall continue in full force and is effect from **November 01, 2021** to **August 31, 2022.**