IPH Bengaluru will provide expert guidance and work with HSTP to deliver the following scope of work:

**Scope of Work**

Working closely with Specialist, India HPSR Fellowship program, one expert faculty from Institute of Public Health Bengaluru will participate in the following activities:

1. Curriculum Revision/Content review for cohort 2022
2. Review panel for screening of Cohort 2022 applications
3. Faculty and Module Lead for Online Module 1
4. Participation as Faculty in Face-to-Face training sessions
5. Participation as HPSR expert in Jury Panels for screening of research proposals
6. Participation in faculty and review meetings
7. Participation as mentors to Cohort 2022 fellows and continued support to Cohort 2021 fellows
8. Participation in 1-2 skill building workshops for Cohort 2021

**Budget**

The total budget for proposed engagement will be INR 600,000 exclusive of taxes.

**Bank Account Details**

|  |  |  |
| --- | --- | --- |
|  | **Name of the Beneficiary** | Institute of Public Health |
|  | **Bank Name** | ICICI Bank Limited |
|  | **Account Number** | 029901000639 |
|  | **Bank Address** | #148/75-1, 26th Main Road, Jayanagar 9th Block, Bangalore-560069 |
|  | **IFSC Code** | ICIC0000299 |
|  | **Swift Code** |  |

**Remuneration**

The entire fee/compensation, not exceeding INR 600,000 exclusive of taxes would be paid to the account mentioned above held by the Institute of Public Health.

**Deliverables, Timelines & Payment Schedule**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Deliverable** | **Time** | **Payment** |
| 1 | Signing of the Contract | January 2022 | INR 240,000 (40%) |
| 2 | Activity report describing the activities performed during Jan 2022 to Jun 2022 and progress on deliverables | June 2022 | INR 180,000 (30%) |
| 3 | Activity report describing the activities performed during contract period Jan 2022 to Jun 2022 | November 2022 | INR 180,000 (30%) |

**Term of Contract**

This contract period is from **January 01, 2022** to **November 30, 2022.** Institute of Public Health will be engaged under the agreement from the date of signing the contract till the date of closure as mentioned above**. The contract will be considered closed when the deliverable is received, and final report is submitted.**