**Annexure I**

**Revised Timelines**

|  |  |  |  |
| --- | --- | --- | --- |
|  |  | **Original** | **Revised** |
| **Grant instalment no** | **Milestone** | **Timelines** | |
| 1 | Signing of contract and submission of the inception report with field plan for qualitative & quantitative research | October 2021 | January 2022 |
| 2 | Completion of qualitative & quantitative data collection and submission of cleaned data | April 2022 | 31 August 2022 |
| 3 | Submission of draft report | June 2022 | 30 September 2022 |
| 4 | Submission of final report | July 2022 | 31 October 2022 |

**Key Dates**

1. The key interim findings, majorly from the qualitative assessment shall be shared with HSTP in the second week of June 2022.
2. Consultation with the Government of Karnataka and stakeholders shall be planned to design/finalize the intervention package in August/September 2022.
3. Dissemination workshop shall be organized in November 2022.