**Revised Timelines and Milestones**

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | October | | | | November | | | | | | December | |
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W 10 | | W 11 |
| Data Consolidation & Analysis | | | | | | | | | | | | |
| Closure on remaining interviews |  |  |  |  |  |  |  |  |  |  | |  |
| Transcripts |  |  |  |  |  |  |  |  |  |  | |  |
| Closure on codebooks |  |  |  |  |  |  |  |  |  |  | |  |
| Report Building | | | | | | | | | | | | |
| Preliminary findings and transcripts with filled codes |  |  |  |  |  |  |  |  |  |  | |  |
| Final report |  |  |  |  |  |  |  |  |  |  | |  |
| Brainstorming on final recommendation |  |  |  |  |  |  |  |  |  |  | |  |
| Incorporating changes and submission of final deport |  |  |  |  |  |  |  |  |  |  | |  |

|  |  |  |
| --- | --- | --- |
| Milestone | % Payout | Amount (INR) |
| Inception Report | 10% | 52,400 |
| Completion of Field Interviews/Data Collection | 25% | 1,31,000 |
| Submission of preliminary findings and transcripts with coding (November 3rd week) | 25% | 1,31,000 |
| Submission of draft of final report [ December 2nd week] | 25% | 1,31,000 |
| Submission and acceptance of Final Report | 15% | 78,600 |
| Total | **100%** | **5,24,000** |