**Scope of Work**

# Project objectives:

1. To develop a comprehensive analysis of the overall policy landscape for cardiovascular diseases (CVDs) care and prevention, identifying gaps in policy and program implementation in Indonesia. Understanding these policy and implementation gaps will serve to elevate public awareness of the growing CVD burden, support evidence-based policymaking, and encourage unified, multi-sectoral action for heart health in the Asia Pacific.
2. ToconceptualizeanddeveloppartnershipswithkeyIndonesianCVDstakeholderstostrengthentheAlliance’snetworksinAsia.

**Timelines:**

1. Research on country profile & policy gaps: April 24, 2023 – May 3, 2023
2. Inputs for regional analysis: May 1, 2023 – May 10, 2023
3. Partnership development: To provide regular weekly updates until December

**Compensation**

The total fee of USD 5,000 will be paid to the consultant upon completion of the deliverables and submission of an invoice to [rajvi.mehta@accessh.org](mailto:rajvi.mehta@accessh.org).

The payment shall be made from the parent Entity ACCESS Health International, INC from the dedicated account kept for ACCESS Health International Southeast Asia Ltd JP Morgan Bank USA.

Please note: ACCESS Health will provide templates for all deliverables described below.

|  |  |
| --- | --- |
| **Scope: Research on CVD policy landscape in Indonesia for APACCVD Alliance** | |
| **Tasks** | **Amount US$** |
| **Research on Country profile**  This initial research and analysis will contextualize the state of CVD in Indonesia:  Conduct structured secondary research using both peer reviewed and grey literature, including scientific articles, policy papers, and white papers or industry papers, with a focus on national policies, programs, and monitoring systems that address the various aspects of heart health.  Identify gaps in policy & program implementation, monitoring and evaluation. A template with specific questions will be provided for information capturing.  The areas these will fall into areas follows:   1. **Country health indicators**    1. Tabulate highlighted country health indicators for CVD (template provided, spreadsheet) based on your research. 2. **Monitoring and Evaluation**    1. Health promotion: What is the participation rate? What results have been achieved? Are there regular audits of programs?    2. CVD Awareness: Are there any programs to monitor awareness of CVD on a periodic basis?    3. CVD Screening: What is the participation rate? What results have been achieved? Are there regular audits of programs? Gaps and challenges? Are any indicators being used to track CVD awareness? | 500 |

**Term**

This engagement shall commence upon execution of this Agreement. The Agreement shall continue in full force and is effect from **April 24, 2023** to **December 29, 2023**.