1. **Scope of Work:**

PricewaterhouseCoopers Services LLP will provide the following services

* Provide inputs and assists in ABDM implementation research
* Providing technical support for implementation of Ayushman Bharat Digital Mission (ABDM) around ABDM 'building blocks' and their 'adoption'.
* Prepare an operational framework to ensure adoption of ABDM by different stakeholders of Healthcare industry especially the standalone clinics, smaller hospitals and diagnostic labs.
* Develop a roadmap for implementation/upgrade/integration of selected HMIS/LIMS across different clinics/hospitals/pharmacies/diagnostic providers.
* Develop a holistic plan to create a system of electronic and personal health records, easily accessible to individuals and healthcare professionals through a consent manager mechanism
* Technical support in planning and implementation of strategies for creation of comprehensive nationwide registries of Health care facilities, Healthcare Practitioners, Drugs and Pharmacies.
* Providing technical inputs for the implementation research being conducted around ABDM adoption.

1. **Deliverables:** PwC will submit a monthly report, along with an invoice, detailing the tasks completed that month.
2. **Fees:** The total fee applicable for this Addendum from October 21, 2023 to April 20, 2024 would be 104,414 USD + OPE (As per actuals) + Tax (as applicable).
3. **Resource Deployment**: A full time Senior Manager level resource with 100% deployment for 6 Months and another full time Consultant level resource with 100% deployment for 6 Months along with Partner level oversight. The resources for the project would be deployed in Delhi NCR area. The resource details are as follows:
4. Dr Rana Mehta, Partner, 2% Deployment (RPH 148 USD) 6 months
5. Dr Shobhit Rastogi, Senior Manager, 100% Deployment (RPH 67 USD) 6 Months
6. Tamanna Sachdeva, Consultant, 100% Deployment (RPH 30.5 USD) 6 Months