# Scope of Work

The consultant will be responsible for the analysis of the quantitative data that was collected across facility assessment and KAP survey done across four north easter states,i.e., Meghalaya, Nagaland, Mizoram and Manipur and:

1. Integrate analysis with the report on Understanding the Barriers And Facilitators To Provision Of Family Planning Services For Young And Low Parity Couples In NE States Of India: A Mixed Methods Study.
2. Building an approach note on how the quantitative analysis was done.
3. Supporting stakeholders to provide clarity on any of the quantitative analyses done or
4. Support any further questions/clarifications or ad-hoc analysis that the investigators may want to support the paper.

# Timelines

The execution is expected to take less than 2 weeks to integrate the quantitative analysis in the Final Draft Report, expected by 28thDecember and final submission by 30th Dec.

|  |  |  |  |
| --- | --- | --- | --- |
| **Sl. No.** | **Detail Items** | **December** | |
| **22nd -23rd** | **26th-30th** |
| **2** | **Analysis of Quantitative Data** |  |  |
| **3** | **Integration of analysis into main report** |  |  |
| **4** | **Submission of Final Report and Project Closure** |  |  |

**Compensation**

The total Consultancy fee for this engagement is INR 80,000. The full payment will be disbursed after the submission of the quantitative analysis.

**Term**

This engagement shall commence upon execution of this Agreement. The Agreement shall continue in full force and is in effect from **December 22, 2022,** to **December 30, 2022.**