Scope of work

Implementation Research to assess capacity of HWCs to deliver comprehensive primary health care

- Our Understanding of the Assignment

The National Health Policy, 20171, envisages Health for All and aims for achieving Universal Health Coverage (UHC).  The Ayushman Bharat scheme was introduced to enable this. It has two components

– the establishment of Health and Wellness Centers (HWC) and the National Health Protection Schemes (NHPS). The intent is to reduce out-of-pocket health expenditure and improve hospital care access for the poor and vulnerable groups2. In April 2018, the Government of India (GOI) launched its first Ayushman Bharat- Health Wellness Centre

(AB-HWC) in Bijappur, Chattisgarh. More than 17,000 HWC were operationalized in the first year, and 1,50,000 HSC and PHCs are to be transformed to HWCs by 2022.

1 See https://www.nhp.gov.in/NHPfiles/national_health_policy_2017.pdf (accessed on October 5, 2020).

2 An assessment of the pilot for the universal health coverage in Tamil Nadu found that the out of pocket expenditure incurred in seeking health care reduced. Also, the catchment area from where the clients accessed the health services expanded; see Muraleedharan V R, et.al (2018): “Universal Health Coverage- Pilot in Tamil Nadu: Has it delivered what was expected?”. IIT Madras, Chennai, Tamil Nadu (accessed on February 29, 2020)

3 Lahariya C. 2020. Health & Wellness Centers to Strengthen Primary Health Care in India: Concept, Progress and Ways Forward. Indian Journal of Pediatrics. July. 2020.

4 Bajpai. N. et.al (2019). Health and Wellness Centres: Expanding Access to Comprehensive Primary Health Care in India. ICT India Working Paper #13. Center for Sustainabile Development, Earth Institute, Columbia University. https://csd.columbia.edu/sites/default/files/content/docs/ICT%20India/Papers/ICT_India_Working_Paper_13.     pdf (accessed on October 5, 2020).

5 Sundarraman. 2018. In new health and wellness centres, India has a good plan for primary care – backed by little action. See https://scroll.in/pulse/870405/in-new-health-and-wellness-centres-india-has-a-good-plan-for-primary- care-backed-by-little-action (accessed on October 5, 2020).

The objectives of the assessment therefore are:

- Understand and assess the process of transformation of HSCs and PHCs to HWCs

  - Understand and assess the inputs provided for the operationalization of HWC, including aspects of Human Resources, Infrastructure, Medicines, Diagnostics, Financing, and IT.

  - Specifically, understand the training needs and inputs that may be needed for the delivery of services.

To identify the bottlenecks in the transformation of HSCs and PHCs to HWCs and

  - their operation.

  - Examine the continuum of care between HWCs and secondary care facilities

  - Monitoring systems.

  - Assess the outputs –the range of services provided6

- Understand the expectations of the community, program implementers, and policymakers and corroborate the key findings

- To establish evidence/produce learnings to inform the policy and programs on HWCs

__________________________________

6 The focus of the Sub-Centres has primarily been on the provision of a restricted set of maternal, neonatal services and delivering few national programs. The ambulatory care provided by them is minuscule. Their transformation into HWCs is as outlined above expected to modify and ensure provision of comprehensive care.

- Approach and Methodology

#### Our Approach

It is proposed to undertake implementation research to assess the implementation and capacity of HWCs in delivering comprehensive primary healthcare services at the State level.

As outlined in the above framework, the research focuses on four aspects – the context, the implementation strategies, the mechanisms for outcomes, and the program outcomes. The assessment of these components is based on the intervention's theory and the intended outcome; and the contextual factors impacting the intervention.

The implementation of any new intervention is likely to be affected by the context. The intervention may also modify the context in which it is delivered. An intervention may have a limited impact either because

_______________________________

7 Peters, David H, Nhan T, Tran & Taghreed Adam (2013), “Implementation Research in Health: A Practical Guide”,

Alliance for Health Policy and Systems Research and World Health Organization, WHO, Geneva

of poor design or implementation. It is also likely that despite a poor design or implementation, a positive outcome may be achieved. Hence, to understand what works, it is proposed to do the following

- The context of the interventions.

- Assess how the intervention is/was being delivered. This would include examining aspects such as logistics and infrastructure systems strengthening initiatives, the digitization processes, health promotion initiatives, and the initiatives for improving service access and how these have impacted the intervention.

- Capture the "fidelity" (whether the intervention was delivered as intended) and "dose" (quantity of intervention implemented) and 'acceptability' (perception among stakeholders about agreeability of the program) and 'coverage' (the degree to which the intended population receives it). Often, interventions undergo some changes when implemented in different contexts. An analysis of the implementation, with the theory of change, would help understand if the interventions were adapted to the context or if the adaptations affected the intervention's fidelity.

- Assess the outcome, primarily by examining the numbers who access the HWCs and the number of clients referred to the higher facilities.

The key aspect of the Implementation Research is that it would inform the intervention process to ensure that interventions impact. The proposed approach is outlined with that perspective. The key steps in the approach include the following:

- Mapping the context, process, and stakeholders helps to understand the context and the theory of change of the intervention, including the outcomes, the stakeholders, roles, and inter- connectedness. Based on discussions with the health department's key stakeholders and others and the desk review, context, process, and the key stakeholders would be mapped.

- Secondary and primary data collection to understand clients' perspectives, providers, provision of inputs, quality of inputs and access, and provision of services. The data would also be used for the bottleneck analysis.

- Adapted bottleneck analysis is a research method used to identify challenges/bottlenecks across the process value chain that impacts the successful implementation of processes. An adapted form of the bottleneck analysis is proposed in this implementation research. For the bottleneck analysis, the four domains that influence services' utilization - supply, demand, quality, and enabling environment would be assessed. Based on this, a process map would be framed with key processes marked. For each of the key processes, the bottlenecks would be identified and mapped.

- Triangulation of all the information to describe the status, challenges, and recommendations for the policy and program on the HWCs.

2.2 Method for data collection

Given the objectives, it is proposed to undertake cross-sectional research. Both secondary and primary data would be used. Primary data would be collected using both quantitative and qualitative approaches.

- Secondary data analysis

The secondary data analysis would include the literature review and the data analysis from HMIS and other sources.

The desk review would include policies, government orders, and guidelines for operationalizing HWCs and academic reports and grey literature on HWCs. The desk review may include, but not limited to:

  - Program proposal, Log frame, if available.

  - Supervision/monitoring reports, MIS reports, timely progress reports, annual outcome surveys.

  - Relevant reports prepared by development agencies, if any

  - Other relevant states, national and international reports

  - Any other relevant published academic or scientific research papers

An analysis of the available program-related secondary data would be done to review the status and performance of the various aspects of the project and identify the indicators for selecting the sample and capacity assessment of HWCs. The major sources of data that would be accessed during the study would include:

  - MIS data for the three states.

  - Data available with concerned government departments at state and national levels8

- Primary Research

A mixture of both quantitative and qualitative methods of data collection is proposed.

The sample of States and the numbers of HWCs that would be studied are detailed out below.

Sample Design

The target sample for the study is the established HWCs in different states since 2018. There are approximately about 48051 HWCs established so far, and they are of a combination of the following types:

- Sub Health Centre (SHC) HWCs

- Primary Health Centres (PHC) HWCs

- Urban Primary Health Centres (UPHC) HWCs

A total sample of 210 HWCs overall is proposed, estimated at 85 percent confidence level and 5 percent margin of error. The sample would be drawn to ensure that it is proportionately representative of the HWC operationalization level, the types of HWCs, and covers the different stakeholders9. The proposed sample design aims to cover HWCs with different types of operational level and geographies composition, and representation of different categories/levels/geographies is illustrated below.

8 Support of IHSC would be sought to access this data

9 Government reports/data will be used to identify the proportion of Sub Health Centre (SHC) HWCs, Primary Health Centres (PHC) HWCs and Urban Primary Health Centres (UPHC) HWCs. In absence of such information equal proportion of facilities will be included in the sample.

Selection of States: The operationalization status of the AB-HWCs differs widely between the states. Accordingly, 1 state each will be chosen from three groups of states – (1) Group having above 80% AB- HWCs operational against the target; (2) Group having 40-80% of operational HWCs against the target; and (3) Group having below 40% of operational HWCs against the target.

The table10 below provides details of the establishment of HWCs against their targets. Based on this, Tamil Nadu, Uttar Pradesh, and Bihar are proposed for the research. The final selection would be made in consultation with the IHSC.

| >80% | 41-80% | <40% |
| --- | --- | --- |
| Maharashtra | Gujarat | Bihar |
| Tamil Nadu | Haryana | Madhya Pradesh |
| Telangana | Karnataka | West Bengal |
|  | Uttar Pradesh | Rajasthan |

Selection of Districts: The sample from each state would be selected from 2 districts. One district far and one close to the state capital would be chosen as the study sample. Thus, the sample HWCs would be drawn from 6 districts in total.

Selection of HWCs: From each selected district, about 35 HWCs would be chosen as the study sample. The HWCs would be proportionately chosen, such that the SHC-HWCs, PHC-HWCs, and UPHC-HWCs are adequately covered in the assessment. A total of 210 HWCs would be assessed.

The sample design would be finalized on mutual agreement with the IHSC team during the inception meeting.

The Assessment of HWCs – Quantitative and Qualitative methods

The facility assessment of the selected 210 HWCs would be carried out in the study by gathering quantitative information covering the following components of the HWCs:

- Various inputs – HR, logistics, infrastructure, digitization, use of telemedicine/IT platform, capacity building, health promotion and linkages with mobile medical units.

- Essential outputs – the creation and maintenance of HWC database, the issuance of health cards and maintaining of Family Health Folders and increased access to services.

The creation of HWCs relies on the engagement of community collectives such as Village Health, Sanitation, and Nutrition Committees (VHSNCs), Mahila Arogya Samitis (MAS), and Self-help Groups (SHGs). The service providers are another stakeholder who has a larger stake at the implementation level. The proposed study would therefore attempt to capture the views of different stakeholders, including the policymakers (state officials), administrators/implementors (State and district officials), implementors (service providers), and the community (VHSNC/MAS member and ASHAs) through in- depth interviews of these representatives in 15 of the sample health facilities. The qualitative sample for the study is detailed out in the below matrix of methods and technical analysis plan proposed.

Sample selection: A list of all the functional HWCs for the selected district will be created based on HMIS and information from Government sites. The required number of samples per district will be selected from this list using a simple random sample selection.

10 Ayushman Bharat Health and Wellness Centres: Accelerating towards Health for All, April 2018 - September 2019.

https://ab-hwc.nhp.gov.in/download/document/340b49eb2c0937e7b79ad8c1d6b975ad.pdf

##### Methodological Tools and Technical Analysis Plan

The key methods, sample, and areas of inquiry for addressing each study's specific objectives are presented in the matrix given below.

| Objective | Proposed methods | Proposed sample | Areas of Enquiry |
| --- | --- | --- | --- |
| Desk Review | Review of program documents, reports, and published literature |  | - Benchmarks/standards and minimum requirements of inputs, outputs, and outcomes – for assessment of performance and capacity - Synthesis of available evidence |
| Secondary data analysis | - Analysis of state MIS portal data - Other state data | - In three states | CPHC inputs, outputs & indicators - HR, Infrastructure, logistics – availability of medicines & diagnostics - Service access |
| Facility assessment | Facility assessment checklist | 210 facilities – HWCs (a proportionate combination of HSC- HWCs, PHC-HWCs, and UPHC- HWCs) | Inputs for HWCs - HR availability - Logistics – essential medicines – stock availability at community & facility levels; diagnostic services – their functionality - Infrastructure – adequate space – for OPD, pharmacy, diagnostic services, display of communication materials at the facility level; spaces for community wellness activities - Digitization – availability of tablets/ smartphones - Availability of telemedicine/ IT linkages – for care provision and virtual training - Health promotion – availability of materials Outputs of HWCs - Availability of HWC database - Availability of Health Cards & Family Health folders - Service access |
| Stakeholder interviews – Service providers | Semi-structured interviews | 30 service providers - 15 HWCs, comprising 7/8 HWCs each from the 2 selected districts , would be chosen to collect qualitative data. - One facility-based MO/MOIC/Mid- | - Roles and services provided – at the facility and outreach - Processes of transformation to HWCs – successes, challenges, adaptations - Use of digital inputs - Use of telemedicine and IT platforms - Perspectives on timely, adequate, and quality of inputs - Perspectives on adequacy and quality of capacity building |

|  |  | Level Provider and one outreach provider – ANM/ASHA, each from 15 facilities would be interviewed | - Health promotion and community mobilization activities undertaken and response - Referral linkages - Perspectives on service uptake and challenges - Perspectives on service quality – gaps and challenges - Perspectives on leadership support; monitoring and review - Data management and reporting |
| --- | --- | --- | --- |
| Stakeholder interview – Community Collectives | Mini-group discussion | 9 discussions with members of community collectives – VHSNC/MAS member or SHG member | - Facilitation of health promotive behaviors and community mobilization activities - Action on inter-sectoral convergence to cover social and environmental determinants |
| Stakeholder Interviews- Program implementers/ officials at the district level | Semi-structured interviews | 6 district officials (one official DPM/ CMO from each district) | - Process of transformation of HSCs and PHCs to HWCs - successes, challenges, adaptations - Perspectives on timely, adequate, and quality of inputs (including HR, infrastructure, capacity building, digitization, IT linkages) - Perspectives on the adequacy of referral linkages (including care through telemedicine) - Perspectives on service uptake and challenges - Perspectives on service quality – gaps and challenges - Perspectives on leadership support; monitoring and review - Data management and reporting |
| Stakeholder Interviews- Policymakers/ officials at the state level | Mini group discussion with 2-3 officials | 3 state officials (1 from each state) | - Process of transformation of HSCs and PHCs to HWCs - successes, challenges, adaptations - Perspectives on the quality and adequacy of inputs - Perspectives on service access and quality - Plans to overcome current challenges |

Consolidated list of proposed primary data collection

|  |  |  | Proposed No. by state |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| S. No | Respondents | Method | State1 | State2 | State3 | Total |
| 1 | State Officials | Semi-structured interview | 1 | 1 | 1 | 3 |
| 2 | District officials | Semi-structured interview | 2 | 2 | 2 | 6 |
| 3 | Facility assessment | Facility assessment checklist | 70 | 70 | 70 | 210 |
| 4 | MO's/MoIC of HWCs | Semi-structured interview | 5 | 5 | 5 | 15 |
| 5 | ANM/AWW | Semi-structured interview | 5 | 5 | 5 | 15 |
| 6 | Community representatives, VHSNCs, PRIs | Mini-group interviews | 3 | 3 | 3 | 9 |

#### Policymaker Engagement Strategy

The implementation research is intended to inform the policy and program. Hence, from the inception of the research, there would be an effort to ensure active engagement with the policy and program stakeholders at the national and state levels. At the national level, the National Health System Resource Center (NHSRC) support would be requested for the study. With the support of the NHSRC, the states would be finalized. The states would be consulted, and their support is taken for the research. The inputs of NHSRC and the State Department would inform the research.

During the research, the key state officials would be kept informed of the research's critical aspects. Topline findings would be shared with each state official. In addition, support of the NHSRC would be requested to organize a dissemination meeting to share the key findings.

After the dissemination, the findings would be shared in the public domain. The research would be published in a refereed journal.

- Proposed Project Personnel

| Personnel |  | Brief profile | Roles and Responsibilities |
| --- | --- | --- | --- |
|  | CORE TEAM |  |  |
| S. Ramanathan Team Lead |  | Ram has more than three decades of experience in health systems research and implementation, community development, and livelihoods: - He has led several large-scale research and consulting assignment including the evaluation of the ASHA program in two states for the NHSRC; evaluation of community monitoring in 9 states for the NRHM, GOI; evaluation of the ARSH program in 9 states; evaluation of home delivery of contraceptives by ASHA; evaluation of AFHCs in 4 states for UNFPA; assessment of the GOI social marketing program for contraceptives, among several others. - He was formerly the state coordinator for UNFPA in Odisha and has supported the implementation of the Integrated Population and Development Program in the state (IPD). He also enabled technical support to enable facility-based maternal and childcare services - He was associated with the Tamil Nadu Health System project and drafted the proposal for leveraging the world bank funding for the NCD | - Conceptualization and finalization of the research framework and methodology - Finalization of framework and plan for secondary data analysis - Inputs and review of tools - Inputs for analysis plan - Report review and finalization |
|  |  | program in Tamil Nadu, during his engagement with the Voluntary Health System in Chennai. |  |
| Vasudha Chakravarthy Co-Team Lead |  | Vasudha has over 10 years of experience of having worked on issues of public health, health systems, gender, and WASH. Some of her achievements are as follows: - She led the rapid assessment of impact of COVID-19 on availability and access to health and nutrition services in five states - She is currently leading evaluations of programs on adolescent reproductive and sexual health. She was the team lead for the implementation research of the Life Skills Education program in Madhya Pradesh. She also led the organizational review of SHSRCs. - She has led assignments on the assessment of VHSNCs, access to family planning services; and is currently also leading an assessment of the access to Maternity Benefit Scheme, Supplementary Nutrition Scheme, and RKSK in Odisha and UP; and a quality audit of a community-based intervention to reduce neonatal deaths in Jharkhand. - She was one of ten global fellows supported by the Harvard School of Public Health to undertake research on Maternal Health. - She has coordinated a 9-state system assessment of the ARSH program of the GOI; and an assessment of the home delivery of contraceptives by ASHAs. - She was part of a team supporting development of health MIS systems for NHM, Himachal Pradesh. | - Oversight for project planning and management - Partner and client management - Finalization of research framework, areas of enquiry - Desk review - Tool development and finalization - Support with training of field teams - Inputs into analysis plan - Qualitative data analysis - Report writing |
| Dr. Prachitha J. Technical Expert – Health Systems |  | Prachitha is development sector professional with over 12 years of experience in areas of public health and health systems research. She has previously worked with Karnataka State Health System Resource Centre (KSHSRC), Institute for Social and Economic Change (ISEC), and TRIOs Development Support as a public health researcher. Some of her notable assignments include: - She was research consultant for the Department of Health and Family Welfare, Government of Karnataka commissioned 'Evaluation of World Bank-funded Karnataka Health System Development and Reform Project'. - As a health economist at KSHSRC she led the gap analysis of implementation of Vajpayee Arogyashree Scheme, Suvarna Arogya | - Technical inputs for finalization of research framework, methodology, primary and secondary analysis plan - Support in desk review - Support in tool development - Support in qualitative data analysis - Support in report writing |
|  |  | program in Tamil Nadu, during his engagement with the Voluntary Health System in Chennai. |  |
| Vasudha Chakravarthy Co-Team Lead |  | Vasudha has over 10 years of experience of having worked on issues of public health, health systems, gender, and WASH. Some of her achievements are as follows: - She led the rapid assessment of impact of COVID-19 on availability and access to health and nutrition services in five states - She is currently leading evaluations of programs on adolescent reproductive and sexual health. She was the team lead for the implementation research of the Life Skills Education program in Madhya Pradesh. She also led the organizational review of SHSRCs. - She has led assignments on the assessment of VHSNCs, access to family planning services; and is currently also leading an assessment of the access to Maternity Benefit Scheme, Supplementary Nutrition Scheme, and RKSK in Odisha and UP; and a quality audit of a community-based intervention to reduce neonatal deaths in Jharkhand. - She was one of ten global fellows supported by the Harvard School of Public Health to undertake research on Maternal Health. - She has coordinated a 9-state system assessment of the ARSH program of the GOI; and an assessment of the home delivery of contraceptives by ASHAs. - She was part of a team supporting development of health MIS systems for NHM, Himachal Pradesh. | - Oversight for project planning and management - Partner and client management - Finalization of research framework, areas of enquiry - Desk review - Tool development and finalization - Support with training of field teams - Inputs into analysis plan - Qualitative data analysis - Report writing |
| Dr. Prachitha J. Technical Expert – Health Systems |  | Prachitha is development sector professional with over 12 years of experience in areas of public health and health systems research. She has previously worked with Karnataka State Health System Resource Centre (KSHSRC), Institute for Social and Economic Change (ISEC), and TRIOs Development Support as a public health researcher. Some of her notable assignments include: - She was research consultant for the Department of Health and Family Welfare, Government of Karnataka commissioned 'Evaluation of World Bank-funded Karnataka Health System Development and Reform Project'. - As a health economist at KSHSRC she led the gap analysis of implementation of Vajpayee Arogyashree Scheme, Suvarna Arogya | - Technical inputs for finalization of research framework, methodology, primary and secondary analysis plan - Support in desk review - Support in tool development - Support in qualitative data analysis - Support in report writing |

|  |  | Suraksha Trust (SAST). She also advocated and supported the development of District Health Action Plan (DHAP) in two districts of Karnataka. Prachitha has a Ph.D is development economics and she specializes in health and public economics. |  |  |
| --- | --- | --- | --- | --- |
| Riza Mahanta Project Manager |  | Riza, a postgraduate in development studies from Azim Premji University, has over 4 years of experience in managing and coordinating projects. She is skilled and experienced in research methodologies and conducting evaluations. She has significant experience in research, evaluation, and documentation and undertaking assignments on public health, maternal and child health, WASH, nutrition, education, and livelihood. - She recently managed a rapid assessment of impact of COVID-19 on availability and access to health and nutrition services in five states. - She is currently managing the third-party audit of 'Facilitating Learning Action Groups' (FLAG) program, which aims to reduce neonatal mortality by up to 33% in Jharkhand for Children's Investment Fund Foundation (CIFF). - She has also coordinated a baseline study on menstrual hygiene management in Uttar Pradesh for WSSCC, UNOPS. |  | - Development of the project execution plan - Resource planning and deployment - Coordination for translation of tools - Finalization of scripting of tools on SurveyCTO - Recruitment of quantitative and qualitative field teams - Training of the field team - Management and coordination of data collection – data quality checks, de-briefs - Management/ coordination of data analysis and report writing |
| R. Vinaygam M&E Manager |  | He brings to the team, the experience of having worked on research and M&E assignments with several organizations including the TISS and 3ie. - Skilled at quantitative and qualitative research and data analytics, he is proficient in the use of STATA and Excel - He led and managed quantitative and qualitative data collection, systematic reviews, and data analysis in: - Assessment of impact of COVID-19 on availability and access to health and nutrition services - Evaluation of Girl Effect Platform and MTV Nishedh in India which aims to provide information about sexual and reproductive health (SRH) among adolescents - Baseline assessment of SHOPS Plus program for Abt Associates on SRH and family planning - End line of HealthRise India evaluation in Shimla and Udaipur, Institute for Health Metrics and Evaluation (IHME) |  | - Finalization of the sampling framework and sample selection protocol - Development of codes for back-end data quality check - Development of data analysis plan - Quantitative data analysis |
| Varun Chakravarthy |  | Varun has over 6 years of experience of having led and managed research and evaluations. He is |  | - Development of framework for secondary data analysis |
| Data Analytics Expert |  | skilled at M&E, data analytics, and the use of big data, location, and geospatial analysis to enable program and policy support. - As the director, Sociometrik, he is at present, leading an assignment to assess flood damage in using remote sensing and quantitative modeling for the Government of Assam. - He is also leading a team providing support to the Niti Aayog in the development of the National Data Analytics Portal. In the past, he has led an assignment to assess the effect of climate change on human development indicators using big data; and sentiment analysis of the odd-even scheme in Delhi using twitter data. - With Development Solutions, Varun led the data analysis - for the Matrix of Change pilot intervention, MTV & GE baseline assessments, baseline assessment of SHOPS Plus program for Abt Associates on SRH and family planning; and assessment of Government initiatives in four states for informing framework for systematic education transformation developed by NITI Aayog. Varun was previously with IDInsight and Indicus Analytics. |  | - Secondary data analysis |
| Ashish Gupta Field Manager |  | Ashish has over 17 years of managing large field teams across India. He has managed field teams in various government-led projects and various international funded projects. He is also skilled in monitoring live data, which helps in maintaining data quality. |  | - Recruitment of field team - Training of the filed team - Field planning - Daily field monitoring and coordination with project manager on addressing any challenges - Ensuring on-field data quality assurance |
|  | SUPPORT TEAM |  |  |  |
| Research associate - 1 |  |  | - Support with desk review - Support with transcription and analysis of qualitative data |  |
| Research analyst – 1 |  |  | - Support with primary and secondary data analysis - Scripting and coding of quantitative tools |  |
| Field supervisors – 3 (one per state) |  |  | - Management of teams and ensuring data collection (facility check list), as per field plan - Addressing any local challenges - Spot checks |  |
| Field investigators – 30 (ten per state) |  |  | - Quantitative data collection (facility checklist) |  |
| Qualitative researchers – 6 (two per state) |  |  | - Semi-structured interactions and mini group discussions |  |
| Note takers – 6 (two per state) |  |  | - Note taking for semi-structured interactions and mini group discussions |  |

- Organizational Capability

Development Solutions is a research and consultancy organization with over six years of experience and has delivered over 60 assignments across 5 countries. It is a partnership firm based in New Delhi, India. In addition to the two partners, there is a research team, monitoring and evaluation team, finance team, and network of consultants.

The team at Development Solutions has more than 30 years of experience in conducting research studies on issues of public health and health systems (adolescent health, SRHR, nutrition), WASH livelihoods, education, and child protection. The in-house team and the network of consultants are skilled in conducting qualitative and quantitative research, data collection, data analytics, M&E, documentation, management, and communication. To meet its clients' needs, the organization pools the collective strengths, expertise, and experience of its team and consultants.

Development Solutions and the proposed team members have undertaken numerous research studies, assessments, and public health and health systems evaluations. Some of the key assignments are as follows:

- Quality audit to assess the implementation of the FLAG program of the Department of Health, Government of Jharkhand. As a part of the program, ASHAs use Participatory Learning and Action (PLA) methods to improve new-born care practices. (Ongoing)

- End-line study to assess the impact of Project Samvaad on the knowledge, skills, and attitudes of SSK & RKSK counselors in Madhya Pradesh for Tata Institute of Social Sciences supported by UNFPA. (Ongoing)

- Evaluation of digital interventions that seek to influence SRH and GBV behaviors among adolescent boys and girls in Rajasthan. (Ongoing)

- A research study to understand acceptability and perceptions on menstrual cups – in association with the University of Liverpool and Tata Trusts (Ongoing)

- Evaluation of pilot programs to enable support for better implementation of Government schemes and programs on Nutrition, Adolescent Health, and Child protection in 4 states in India. (2020)

- Assessment of Contraceptive Social Marketing Program of Government of India supported by UNFPA. (2019)

- Implementation research for the Life Skills Education program in Government schools in Madhya Pradesh, supported by UNFPA (2019)

- Evaluation of the HealthRise program, as a local evaluation partner of the IHME in two states in India. (2018)

- Assessment of Adolescent Friendly Health Clinics, in 4 states, supported by UNFPA. (2017)

- Study on the quality of family planning services provided in Government Health facilities in Jharkhand supported by Jhpeigo. (2016)

- Organizational review of State Health System Resource Centres (SHSRCs), for the NHSRC (2015)

- Assessment and analytical documentation of Community based strategy for addressing HIV in Andhra Pradesh, for Hindustan Latex Family Planning Promotion Trust (HLFPPT). (2014)

- Assessment of the scheme for Home delivery of contraceptives by ASHA's for the MoHFW, Government of India, supported by Population Foundation of India. Based on the findings of the assessment, the program was scaled up from its pilot phase. (2012-13). (undertaken by the partners in their previous role)

- Assessment of the Adolescent Reproductive and Sexual Health Program of the Government of India, across 9 states, supported by Ford Foundation. As a part of the study, national and state consultations were conducted that were attended by several officials from the Ministry of Health and Family Welfare, New Delhi, as well as from several state health departments including Gujarat,

- Maharashtra, Jammu & Kashmir, Meghalaya, Odisha, Rajasthan, West Bengal, and Bihar, (2012). (undertaken by the partners in their previous role)

- Assessment of the ASHA Program in Chhattisgarh and Jharkhand for NHSRC. (2007)

Sociometrik Infer Pvt. Ltd.

Sociometrik was founded out of the vision of providing technology-driven solutions to address public policy challenges worldwide. The organization's work brings together remote sensing, location- intelligence, and big-data analytics with traditional economic modeling and robust evaluation design models.

Sociometrik has a multi-disciplinary team of economists, geospatial analysts, data scientists and policy analysts who have worked with governments, multilateral organizations, and global corporates for over 30 years cumulatively.

Some of the key assignments of the organization, include:

- Data partners for the Niti Aayog flagship initiative – the National Data Analytics Portal and are working with data from 250 ministries across states to create a shared data warehouse from 250 ministries across the states (ongoing)

- Data partners for the Delhi and Indore war rooms for Covid-19 (ongoing)

- Flood detection and damage assessment using remote sensing and quantitative methods, for the Government of Assam

- Secondary and primary data analysis to assess the awareness and uptake of the maternity benefit and supplementary nutrition schemes in Odisha; and identifying the effect of distance from nearest health facilities and banks (using location analytics) on uptake of and access to the scheme

- Analysis of large-scale Government administrative data from four states to inform the Niti Aayog Education System Transformation Initiative

- For the Dr. Ambedkar International Center, they used geo-simulation techniques, layered with location and secondary data analytics to identify additional schools needed and optimization of transport allowance

- under the Sarva Siksha Abhiyan to enhance school access. They also used a combination of GIS tools, primary and secondary data to create a predictive model for school access, using artificial intelligence modules

- Analytics on the effect of climate change on human development indicators, for UNDP

- Roof classification and demand pocket estimation using machine learning and econometric modeling, for Accenture

Over the last two years, the two organizations have been working together on several assignments. This includes evaluation of pilot interventions on nutrition and adolescent health; evaluation of digital interventions on adolescent reproductive and sexual health; digital evaluation of a pilot program that seeks to shift online narratives among young persons on reproductive health, girls' empowerment, and air quality; assessment of educational transformation initiatives in four states, presented to Niti Aayog; among others.

Together, the two organizations bring skills and experience in:

- Public health and health systems research, using both primary and secondary data

- Extensive experience of having worked across states in India

- Expertise in qualitative and quantitative research methods; and data analytics

- A vast network of consultants and partner organizations across states

Development Solutions and Sociometric have worked across the states in India. Development Solutions has also done international assignments in Afghanistan, Bangladesh, Cambodia and Sri Lanka.

| Government Institutions | - National Health System Resource Centre (NHSRC) - HLFPPT (Hindustan Latex Family Planning Promotion Trust) |
| --- | --- |
| UN Agencies | - United Nations Children's Fund (UNICEF) - United Nations Population Fund (UNFPA) - International Labor Organization - Water Supply and Sanitation Collaborative Council, UNOPS |
| International NGOs/ Philanthropies | - American India Foundation - IPE Global - Freedom Fund - Aga Khan Foundation - SOS 'Children's Village - Sanitation First - Children's Investment Fund Foundation - Michael and Susan Dell Foundation |
| Indian NGOs/ Philanthropies | - Centre for Advocacy and Research - Centre for Responsible Business - Freedom from Hunger India Trust - Foundation for Rural Recovery and Development (FORRAD) - Score Foundation - SRHR Alliance - Quest Alliance - Voluntary Health Services - Jan Sahas |
|  | - Central Square Foundation - Azim Premji Philanthropic Initiatives (APPI) - WaterAid India |
| Corporate Sector | - Centum WorkSkills India - Maccafferi India - Microsoft - MilIndia - Boston Consulting Group |
| Research & Consultancy Organizations | - Abt Associates India - The George Institute for Global Health |
| Academic Organizations | - Tata Institute of Social Sciences (TISS) - University of Liverpool - Monash University Australia |

- Project Management and Supervision

As outlined in the proposed personnel matrix, the project manager's execution would be managed by the project manager, with support from the Co-team lead.

- A detailed project execution and resource plan would be developed before the project's initation and populated on the internal project management dashboard at Development Solutions. The dashboard enables close tracking of timelines and deliverables.

- The Co-team lead would support and monitor the project execution to ensure adherence to timelines and quality assurance protocols

- The Team Lead, Health Systems expert, M&E Manager, and Data analytics experts would undertake specific technical roles within the project, including conceptualization and finalization of the research framework and areas of inquiry, finalization of sampling framework, tool development, secondary and primary data analysis and report writing

- The project manager would be supported by the field manager in the planning and management of field processes

- She would be supported by the administrative and operations team at Development solutions in ensuring translation and scripting of tools, recruitment of field teams, and qualitative researchers.

| Technical roles | Team Lead, Health Systems Expert, M&E Manager, Data analytics expert, Co- team lead |
| --- | --- |
| Management roles | Project Manager, Co-team lead, field manager |

#### Field management

Development Solutions has vast experience in managing assignments that require large quantitative and qualitative sample data collection. The organization has established systems of field reporting and data quality checks, which are outlined below:

- A detailed field execution plan, both for quantitative and qualitative data collection, would be developed to guide the field data collection

- The quantitative data collection would be done electronically, and submissions and sample completion would be monitored at the end of each day by the project manager

- As outlined in the graphic, a data quality check on submitted data would be done each day and a feedback report shared with the field manager. Completed samples, by investigators submitted by the field manager in the de-brief report, would be cross-checked with the online submissions.

- A data quality check code would be developed to monitor the completeness of data submitted, time of submission, the average time of completion, and investigator efficiency. Outliers, if any, would be flagged to the filed manager

- Daily de-brief calls between the field supervisors and the field manager, and the field manager and project manager would enable quick communication and resolution of challenges. The calls will also help to discuss data collection progress, as per the field plan and any feedback based on the back- end data quality checks.

- The qualitative teams would submit daily WhatsApp updates to the project manager, and de-brief calls would be done every alternate day with each of the teams

- Documentation templates would be developed for qualitative data documentation – the note- takers would provide detailed notes, as per the documentation templates.

- Also, the teams would be expected to record qualitative interactions, given consent, and feasibility. At least 10 percent of the recordings will be cross-checked with the notes to ensure quality and consistency.

Partner management and communication

As mentioned earlier, in the proposal, Development Solutions and Sociometrik have worked together on several assignments. For this project, it is understood that Development Solutions would be the primary/ lead partner, who would be responsible for overall project management and execution. Sociometik would support with the secondary data review and analysis and the primary data analysis, as may be needed.

The following mechanisms for coordination and process efficiencies would be followed:

- Internal project coordination meeting on the award of the project – to discuss and finalize the roles, deliverables, resource allocation, communication, and coordination mechanisms

- Roles, deliverables, and resource allocation at both organizations would be clearly defined following the meeting and documented in the project execution plan

- The project execution plan would be shared on a common google doc to enable easy review and monitoring by both organizations. A provision for a status update against tasks would be created to enable transparent viewing of the status of the project by each organization

- Key team members from both teams would be marked on all emails – as per communication protocol decided during the initial project coordination meeting

- Weekly standing calls/ meetings – for a joint review of project progress and discussions on project activities (as may be needed)

- The Co-team lead (from Development Solutions) would be the point person for all communication with the partner organization (Sociometrik) – to ensure clarity and consistency in communication

Conflict and issue resolution – It is proposed that:

- Issues and challenges, if any, be openly discussed during the weekly calls/ meetings; and joint resolutions be arrived at

- In case of any issue that is unresolved during the weekly calls/ meetings, the Co-team lead from Development Solutions (who is also a founder and partner of the organization), would speak with the director(s)/ key personnel at Sociometrik to enable a quick resolution

- Finally, a team of three independent personnel, one from each organization (not involved with the project) and a third neutral member would be established to enable resolution of issues/ conflicts

- Implementation Plan, Quality Assurance, and Timelines

6.1 Implementation Plan

PHASE 1 – PREPARATORY ACTIVITIES

Inception Meeting

An inception meeting would be held at the start of the project, with the team at IHSC to discuss the research framework, areas of inquiry, and management, and execution of the project. The meeting would also be used as an opportunity to define communication protocols and deliverables for the project.

Desk review and secondary data analysis

Desk review of the available program documents, government orders, operational guidelines, and reports would be undertaken. The MIS data and other State-level data would also be analyzed, as outlined earlier in the proposal. A framework would be developed to guide the desk review and secondary data analysis.

Finalization of the research framework, areas of inquiry, and sampling methodology

Based on the inception meeting, desk review, and secondary data analysis, the research framework would be finalized. The sampling methodology and sample selection process would be refined.

Internal planning for execution

An internal project execution and resource plan would be developed. Processes for recruitment of field teams and qualitative researchers would be initiated. An initial meeting would be held with the partner organization to finalize roles, deliverables, and communication mechanisms.

The final research outline document would be shared, outlining the finalized approach, areas of inquiry, sampling, and assignment execution.

Development of Study Tools, Translation, and Testing

Based on the desk review, finalized research framework, and inquiry areas, the study tools would be developed – both quantitative (structured and semi-structured) and qualitative. The quantitative tools would be translated and back-translated to ensure quality and consistency. It would then be scripted and coded onto a CAPI platform (SurveyCTO). The quantitative tools would be pre-tested in all three states. The pre-testing would focus on the ability to convey the question, comprehension, unwillingness, or hesitation of respondents, availability of needed data at the facility level, and the questions' relevance. The logical flow would be assessed along with the time taken to complete the response. Based on this, any changes required in the CAPI version would be made.

The tools would be scripted in SurveyCTO, which ensures data security through encryption, quality monitoring, including time auditing, minimize the errors through logics and enable visualization of data. One day’s rigorous testing of the app and tool would be done internally by the team before pre-testing the field's tool.

The draft tools would be shared with IHSC for feedback, and the final tools post-pre-testing would also be shared.

Recruitment and Training of Study Team

The field team's engagement follows prescribed protocols such as a CV review to assess prior experience, interviews, and reference checks. A mix of male and female investigators would be chosen, who would be well conversant in the study states and districts' local dialects and customs. In addition to the core team, qualitative researchers would be engaged from the consultants' panel, with Development Solutions.

A three-day training for the quantitative team would be undertaken. The training would focus on familiarisation with tools, sensitivity to the respondents, use of SurveyCTO, and adherence to ethical processes. Mock practice sessions would be undertaken. The third day of the training would be used as a field practice, where the team would be taken to non-sample facilities to practice data collection in field conditions. The final selection of the team would be made based on the post-training evaluation.

Also, a two-day training would be undertaken for qualitative researches and note-takers. The training would provide an overview of the study objectives and methodology, context and overview of the qualitative tools, and ethical processes. During the training, processes of field management and documentation would also be explained.

PHASE 2 – DATA COLLECTION AND ANALYSIS

Data collection

A detailed field execution plan would guide the data collection. It would outline the tasks (samples to be achieved), roles Quality in data collection would be ensured through supervisors and the field manager.

- For the facility assessment, a team of 10 investigators per state and field supervisors (one in each state) would undertake the data collection.

- The supervisor will be responsible for the team's supervision, conducting debriefs every day, ensuring data quality, and adherence to all ethical protocols. The supervisor will conduct at-least 20% spot checks of the facility assessment data collection.

- Six teams of qualitative researchers and notes takers – two in each state would undertake the semi- structured interactions with the service providers and mini-group discussions

- The core-team would undertake interactions with state and district officials for the assignment

Data Processing and Analysis

- As mentioned in the management and supervision section of this proposal, quantitative data, gather and submitted electronically, will be checked daily at the back-end. A quality code for data quality check would be developed for the same

- An analysis plan would be developed to guide the quantitative data collection

- For the qualitative data collection, researchers would be expected to record interactions, where feasible, and upload it onto a secure google drive location – allocated by Development Solutions within 2 days of the interaction

- Notetakers would be provided with documentation templates to enable detailed notes.

- The qualitative data would be thematically analyzed.

PHASE 3 – REPORT WRITING

A detailed report structure would be developed to guide the report writing. A draft report will be shared with key team members at IHSC for their feedback and suggestions. A presentation of the findings would be made to the policymakers and relevant stakeholders.

Quality Assurance Mechanism

The following are the stages involved in the quality assurance mechanism to be undertaken by the team members

| Stages | Mechanism |
| --- | --- |
| Overall management and communication | - The roles and responsibilities of the team members and partner organization would be well defined at the start of the project; communication channels and protocols will be defined - Development of detailed project execution plan and resource plan - Weekly calls/ meetings between the proposed partner organizations - Regular updates to IHSC in the progress - A close-out procedure after completion of the assignment which may include a post-project review to review |
| Pre-data collection | - A rigorous process of recruitment ensuring experienced and qualified team. Preference would be given to those who have worked with Development Solutions in the past - A gender-balanced team. - Supervisors would be those who have worked with Development Solutions in the past and are familiar with our quality control and reporting protocols - Rigorous three-day training, including mock sessions and field practice. Final selection of the team post-training evaluation - Review of the instruments for data collection. - Translation and back-translation of the instrument. - Undertake pre-test using the electronic data instrument. - Test the data collection, transfer, and management plan during the pre-test - Providing field kits to all field researchers with all project details, field plans, consent forms, hard copies of the tool, checklists. |
| Data Collection | - Established channels of communication, reporting, and troubleshooting. - Assessing the field team’s ability and post-training evaluation for the filtering of the field team. - Communicate to the field investigators the quality expectations. - Supervisors to enable support, coordination, and quality assurance. At-least 20% spot checks of facility assessment data collection. |
|  | - Daily debriefs- one in the morning for daily check of field kits and tablets and one in the evening to discuss field challenges. - Leveraging technology actively. - Detailed fieldwork plan with timelines, milestones developed. - Quick communication of any field issues that would have an impact on data collection. - Digital back checks of random to ensure data integrity. - Ensuring regular data transfer from the handheld to the server. - Monitor the data transfer daily. - All team members, including the data entry team to be briefed on data security norms. - Recording of qualitative interactions - At-least 10% recordings cross-checked with notes to ensure completeness and accurary |
| Electronic Data Monitoring | - Reviewing - Surveyor level trends - Geography level trends - Capturing anomalies in the data - Inflation of sample to ensure clean and filtered data. - On Survey CTO, reviewing automated skip patterns, constraints, hints, completion of each survey, and encrypted data. - Daily data validation before uploading surveys. - Daily review of monitoring templates and trackers shared by Development Solutions. |
| Writing of Report | - Brainstorming meetings to discuss the analysis and report structure - Writing plan/guide to be developed for the team to ensure that each member ensures that key aspects to be covered are listed, for each section/chapter - Standardization of fonts, use of acronyms, and format. - Use of illustrations and graphics as required. - The draft report structure and the report will be shared with IHSC to get their feedback and suggestions, which will be incorporated in the final report. |

Ethical Considerations

- All teams will be trained extensively on ethics and adverse events during data collection. The following regulations and guidelines governing research ethics will be followed:

  - Informed consent will be ensured through voluntary informed consent from all respondents.

  - Voluntary participation and no coercion, undue influence or inducement, or intimidation will be used.

- The following rights of respondents will be ensured:

  - Informed consent - Informed consent would be sought and recorded for every interview/ survey questionnaire.

  - Refusal - The respondents would be informed and made to understand that they have the

right to say “NO” and they can exercise this right at any time during the survey.

  - Privacy – It will be ensured that the respondents are comfortable, and the survey is conducted in a private space.

  - Accurate representation - The purpose of the research will be clearly explained to the respondents.

Implementation Activities and Timelines

| Sl No. | Activities | Timelines (in months and fortnights (FN)) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Month 1 |  | Month 2 |  | Month 3 |  | Month 4 |  | Month 5 |  | Month 6 |  |
|  |  | FN 1 | FN 2 | FN 3 | FN 4 | FN 5 | FN 6 | FN 7 | FN 8 | FN 9 | FN 10 | FN 11 | FN 12 |
| Phase - 1 Preparatory Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Inception meeting with IHSC |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Secondary research/desk review - review of program documents, GOs, reports & other literature; and secondary data |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Classifying reports available |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 | Internet search for documents |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 | Desk review of reports and documents |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4 | Map stakeholders and linkages |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5 | Drafting desk review report |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Analysis of MIS of three states |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | Identifying the relevant MIS & getting requisite permission for their use |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 | Analysis of the MIS |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Finalization of the research framework, sampling plan, and the areas of inquiry |  |  |  |  |  |  |  |  |  |  |  |  |
| D1 | Research outline document incorporating key questions for the research, research outcomes and plans for data collection |  | X |  |  |  |  |  |  |  |  |  |  |
| 5 | Development of data collection tools |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 | Drafting tools |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2 | Sharing draft tools with IHSC |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3 | Feedback incorporation and finalizing tools |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.4 | Translating tools |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.5 | Pilot testing of tools |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.6 | Modifying tools |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.7 | Sharing revised and final tools with IHSC |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.8 | Scripting quantitative tools for electronic capture |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.9 | Testing for data collection |  |  |  |  |  |  |  |  |  |  |  |  |
| D2 | Submission of finalized study tools |  |  |  | X |  |  |  |  |  |  |  |  |
| 6 | Hiring & training of field team |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 | Identifying field team for data collection |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2 | Interviewing prospective candidates & shortlisting |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.3 | Developing a training plan/ module |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.4 | Organising training |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.5 | Finalising field team post training |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.6 | List of Field Team shared with IHSC |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase - 2 Data Collection, Processing, and Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Quantitative and qualitative data collection |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.1 | Facility assessment |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.2 | Semi-structured interviews with key stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.3 | Mini-group discussions with community representatives |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | Data entry, processing, and analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.1 | Data cleaning |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.2 | Tabulation plan |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.3 | Quantitative data analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.4 | Qualitative data analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase - 3 Report Writing and Dissemination |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | Development of the report |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.1 | Drafting report |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.2 | Sharing draft report with IHSC |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.3 | Comments from IHSC |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.4 | Revision of report based on comments |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | Presentation of the findings |  |  |  |  |  |  |  |  |  |  |  |  |
| D3 | Submission of the final report |  |  |  |  |  |  |  |  |  |  |  | X |

- CVs of the Proposed Team

| Name | S. Ramanathan |
| --- | --- |
| Proposed position in the team | Team Lead |

| College/university | Year of Completion | Degree(s)/Diploma(s) obtained |
| --- | --- | --- |
| Jawaharlal Nehru University, New Delhi | 1985 | M. Phil (Applied Economics) |

Professional Experience: 32 years

| Period | Organization/ Title | Summary of activities performed |
| --- | --- | --- |
| March 2014 to present | Partner, Development Solutions | Team leader for multiple projects at Development Solutions in areas on public health, sexual and reproductive health, adolescent related issues, education, and livelihood. Some examples are: - Support for Consultation on the National Health Policy 2015, for National Health Systems Resource Centre (NHSRC) - Organizational Assessment of the State Health System Resource Center for NHSRC - Assessment of Adolescent Friendly Health Clinics, UNFPA - Assessment of Contraceptive Social Marketing (CSM) program by GOI for UNFPA - Assessment of Community based Strategy for addressing HIV in Andhra Pradesh, for Hindustan Latex (HLFPPT) - Gap Analysis of the RMNCH+A strategy for SRHR Alliance - Assessment of PLHIV and ART linkage (PALS) software for VHS-CDC - Situation Analysis on COVID-19 impact on economic units and workers in formal and informal economy for International Labor Organization - A Dipstick Study on Employment of Persons with Disabilities in the BFSI Sector in Covid-19 Scenario for American India Foundation - Baseline Assessment of SHOPS Plus Project by Abt Associates - Evaluation of A Group of Pilot Interventions (Matrix of Change) Across Nutrition, Adolescent Health, And Child Protection, supported by CIFF - Baseline Research on Critical Appraisal Skills for Public Health Reporting and Communication for Routine Immunization; supported by George Institute of Global Health, Oxford University and UNICEF - Technical documentation of a cross-sector integration model to address issues of nutrition among women; for Freedom for Hunger India Trust |
| Period | Organization/ Title | Summary of activities performed |
|  |  | - Operational plan for strengthening of VHSNCs in UP, for World Vision - Qualitative study on Child Labor in mining in Kota-Bundi districts of Rajasthan, for Centre for Responsible Business - Assessment of the Programme for ‘Children in Contact with Railway Stations’ (CCRS) for Azim Premji Philanthropic Initiatives - Feasibility assessment of livelihood situation and opportunities in four states for Save the Children - Evaluation of Freedom Fund’s “Pathways” Case Management Project - Midline and End Line Assessment of 'Child Labour Free Jaipur' Hotspot Program supported by Children's Investment Fund Foundation (CIFF) - Independent review of impact data of the Freedom Fund in southern India ‘Hotspot’ program - Study on productivity & working conditions in natural stone mining industry supply chain, Rajasthan for International Labor Organization - Baseline assessment of the Jaipur Hot Spot Project on child labor, Freedom Fund - Household survey, 1000 households in Bap Tehsil, Jodhpur - Value Chain Analysis of Dry Fruits in Afghanistan; Aga Khan Foundation, Afghanistan - Project management support for the implementation of CSR interventions in Bap Tehsil, Jodhpur - Implementation research of Umang Program by UNFPA - M&E on General Employability Skills Training in Delhi Schools, Quest Alliance - Development of an M&E Framework for Microsoft - Social and Behavior Change Communication for Urban Sanitation and FSSM in Delhi; Water Aid India, IWMI and Cure - Strategy for Youth Development- Cambodia and Sri Lanka; SOS Children Village International - Strategy for Community Development & livelihoods in Bap Tehsil, Jodhpur, Rajasthan - Project Management Support for Skill Development Program in Kerala - Strategic development and technical documentation for skilling visually impaired persons across India, for SCORE Foundation - Business Development & Organizational building |
| June 2010 to February 2014 | TRIOs Development Support (P) Ltd Director | Team leader in multiple projects including: - Survey on child labor in Garment Industry in Delhi for Save the Children - Baseline Survey for Strengthening prevention, prosecution and protection services for children at risk of |
| Period | Organization/ Title | Summary of activities performed |
|  |  | or subjected to trafficking for labor in Andhra Pradesh and Bangalore in India - Strategic Plan for LEPRA, India; for 2013-15 - Training of 120,000 members of the Mothers & Jaanch Committees of Women and Child Development Department in Odisha - Adolescent Reproductive and Sexual Health to Develop Operational Frame work and Road Map for Adolescents Friendly Sexual and Reproductive Health Services in India - Implication of Sanitation and Hygiene on Polio Eradication Initiatives in 10 High Risk Blocks in Meerut, Muzaffarnagar & Moradabad Districts - Project on Market Survey of Livelihood Opportunities for Youth in Orissa - Project Need Assessment and Mapping of the Livelihood Opportunities for Adolescent Girls in Selected Districts of Bihar - Preparation of CSR Master Plan for Kymore, MP - Capacity Building Expert in Bihar for UNICEF supported project. - Consortium Coordinator & Capacity Building Expert for NREGS, Gujarat- State Resource Centre, MGNREGS, Gujarat |
| 2009 to 2010 | AIDS Prevention & Control Project, Voluntary Health Services Director, Strategic Planning & Partnerships | - Developed the annual plans for the APAC - Support for development of TI’s - Coordination between the health system and TNSACS - Facilitating interface and integration with Tamil Nadu Health System Project and NRHM. - Facilitated the preparation of the Project Implementation Plan (PIP) for Additional Financing from World Bank for TNHSP. - Facilitated the preparation of the scale-up plan, for the prevention & mobilization through Labor, education and rural development departments for CVD, Diabetes, Cancer and breast cancer in the entire state of Tamil Nadu, for TNHSP. - Developed concept note for establishment of Data Resource Centre for TNHSP - Development of Communication Strategy for NRHM, Tamil Nadu. |
| 2007 to 2009 | Independent Consultant | - Strategic Plan – I-TECH India, (for human and institutional capacity building for HIV prevention, treatment and care). - Team Leader, Review of Community Monitoring in 9 states, for Advisory Group on Community Action, NRHM, Government of India - Member, Research Team, Costing of Maternal Health Services, ARTH, Rajasthan - Team Leader, Preparation of State NRHM, PIP (2008-9) |
| Period | Organization/ Title | Summary of activities performed |
|  |  | - Assessment of ASHA Program, Chhattisgarh, for NHSRC, New Delhi. - Assessment of ASHA Programme in Jharkhand for NHSRC, New Delhi. - Visiting Faculty, School of Public Health, SRM University, Chennai; taught courses on Health Economics, Financing, Gender& Health. - Visiting Faculty, Asian Institute of Public Health, Bhubaneswar - Analytical documentation of Livelihood Opportunities, Post Tsunami for Plan International - Member, Evaluation of Tsunami Response Program in Tamil Nadu, Plan International |
| 2007 | Government of Bamyan & Aga Khan Foundation, Strategic Planning Advisor | - Prepared a five-year development plan for Bamyan province, involving an estimated budget of $ 50 million per annum, to identify and prioritize projects in community development, health, education, private enterprise development, energy, water, and women’s affairs. The projects form the blue print for development policies for the province from 2008 to 2012. |
| 2005 to 2006 | Aga Khan Foundation Rural Development Coordinator | Coordinated community development & livelihood interventions in Badakshan province, in about 200 villages, in the context of enabling alternative livelihood for poppy growers. |
| 1999 to 2005 | United Nations Population Fund State Program Coordinator, Orissa | Worked with the Government of Orissa for a result-based implementation of an Integrated Population and Development Project. |
| 1996 to 1999 | Independent Consultant | - Co-author, Women and Panchayati Raj in Rajasthan. Institute of Social Studies Trust, Bangalore, - Team Member, Evaluation of NGO-GO Relations in Rajasthan and publication Relations of Significance: NGO-GO Relation in Rajasthan. PRADAN - Team Leader, Missing Links: Women and Agriculture in Rajasthan. Case Studies in Udaipur and Bikaner Districts, Rajasthan. Report Submitted to Ford Foundation, New Delhi |
| 1994 to 1995 | URMUL Trust, Rajasthan; Researcher | - Worked on Livelihood issues and part of the team for establishing a research center to work on issues of Arid Zones |
| 1990 to 1993 | Institute of Development Studies, Rajasthan; Associate Fellow | - Team Member, Urban Water Supply in Rajasthan - Equity and Productivity Issues in Indira Gandhi Canal Project: A Review of Literature - Mid-term Review of the Land and Water Resources Programme of Gramin Vikas Samiti - Indigenous Water Harvesting Systems in Rajasthan |
| 1989 to 1990 | Centre for Science & Environment Research Associate | - Team Member, publication on Dying Wisdom: State of India’s Environment – a Citizens Report - Research on Indigenous water harvesting systems in India |

Paper presentations and Publications:

- S. Ramanathan, Vasudha Chakravarthy. Structure of opportunities for adolescents – Policies and Programs on adolescent health in India. Published in book – Empowering Adolescents, 2017

- S. Ramanathan, Vasudha Chakravarthy. Child Labor in Global Production Networks: Evidence from two Industries; presented at the National Conference on Rural Transformation in India: Issues, prospects and challenges, Institute of Development Studies, Jaipur; December 4-6, 2014

- Vasudha Chakravarthy, S. Ramanathan. Access to maternal health services: understanding where and why women access services for pregnancy and delivery. Abstract selected for presentation at the India International Public Health Conference, Kerala; November 6-7, 2014

- S. Ramanathan, Vasudha Chakravarthy. ARSH service provision in Public Health Facilities in India: An assessment and an alternate framework to enhance access. Abstract selected for presentation at the India International Public Health Conference, Kerala; November 6-7, 2014

- Kavita Srivastava, S Ramanathan & Purwa Kushwaha; Women and Panchayati Raj in Rajasthan. Institute of Social Studies Trust, Bangalore

- S. Ramanathan. Sustainable Development in Arid Zone Rajasthan, India: The role of Rain Water Harvesting systems. Abstract selected for presentation at the International conference on Rainwater Catchment Systems. Tehran I.R. Iran; April 21-25, 1997

- S. Ramanathan, Sanjoy Ghose. Irrigation Management Turnover: A users Perspective – the case of the Indira Gandhi Canal, Rajasthan; paper presented in Workshop on Irrigation Management Turnover, International Irrigation Management Institute, Wuhan, P.R. China; 20-24 September 1994

- M.S. Rathore, S. Ramanathan, Ratna Reddy. Urban water supply in Rajasthan: problems and prospects; August 27, 1994, Volume 29, No. 35, Economic and Political Weekly

- Ramanathan. S. Rajasthan’ sorrow: Report of workshop on Indira Gandhi Canal; August 3, 1991,

- Volume 26, No.31-32, Economic and Political Weekly

- Ramanathan. S. Greening the desert the Israeli way: is it good economics; February 26, 1994, Volume 29, No.9, Economic and Political Weekly

#### Language Skills:

| Language | Reading | Writing | Speaking |
| --- | --- | --- | --- |
| Hindi | Excellent | Excellent | Excellent |
| English | Excellent | Excellent | Excellent |
| Tamil | Excellent | Excellent | Excellent |
| Malayalam | Proficient at conversing |  |  |
| Oriya | Ability to comprehend spoken Oriya. |  |  |

| Name | Vasudha Chakravarthy |
| --- | --- |
| Proposed position in the team | Co-Team Lead |

Education:

| College/university | Dates Attended | Degree(s)/Diploma(s) obtained |
| --- | --- | --- |
| SRM University, Tamil Nadu | 2010 | MPH – Master’s in Public Health |
| Delhi University | 2008 | B.Sc. (Honours.) – Applied Zoology |

Core Competencies:

- Program Monitoring & Evaluation

- Qualitative Research

- Documentation & Strategy development

- Project Management

Areas of Specialization:

- Reproductive and Sexual Health and Health Systems

- Gender

Years of Professional Experience: 10 years

Professional Experience:

| Period | Organization/ Title | Summary of activities performed relevant to the Assignment |
| --- | --- | --- |
| March 2014 to present | Partner, Development Solutions | Led multiple assignments including: - Perception Survey to Understand Barriers and Enablers to Girls' Secondary Education in Rajasthan Post COVID-19 for IPE Global - Rapid assessment on impact of COVID-19 on availability and access to health and nutrition services for children, adolescents and women, supported by Population Foundation of India - End-line study to assess the impact of the project Samvaad on the knowledge, skills and attitudes of SSK & RKSK counsellors in Madhya Pradesh for Tata Institute of Social Sciences (TISS) - Evaluation of Girl Effect Platform and MTV Nishedh in India; to enable SRH Knowledge and nudge behaviors, supported by CIFF - Evaluation of Matrix of Change, micro pilot, on Adolescent health, nutrition and child protection, supported by CIFF - Third Party Assessment of the FLAG Program (a community based participatory intervention on neonatal health) in Jharkhand, supported by CIFF; results presented to NHM Jharkhand, in consultation with Ekjut (implementing partner) - Baseline and End-line assessment – Integrated response to reduce prevalence of child marriage in India, SRHR Alliance - Strategy on addressing SRH issues of persons with hearing disabilities, Deaf Child Worldwide - Implementation research of Life skills education program in Madhya Pradesh, for UNFPA - Assessment & Validation of Impact under the Systemic School Education Transformation Programs in 4 States, Micheal and |

| Period | Organization/ Title | Summary of activities performed relevant to the Assignment |
| --- | --- | --- |
|  |  | Susan Dell Foundation (MSDF), in association with Samagra Governance and Niti Aayog - Process Evaluation of the Adarsh Vidyalaya Yojna in Rajasthan for MSDF, presented to State Government Rajasthan - Evaluation of ABL Program in Gujarat, for Central Square Foundation (CSF), presented to Government of Gujarat - Evaluation of Early Childhood Education Programs in Gujarat and Karnataka, for CSF - Evaluation support for the Health Rise Program for Institute of Health Metrics and Evaluation - Baseline on MHM in 5 districts of UP, for the WSSCC, UNOPS - Assessment of PLHIV and ART linkage (PALS) software for VHS- CDC - Organizational assessment of State Health Resource Centers for NHSRC - Operational plan for strengthening of VHSNCs in UP, for World Vision - Consultation on the National Health Policy 2015, for National Health Systems Resource Centre (NHSRC) Other projects: - Assessment and documentation of processes for the development of a software for linkage of PLHIV and ART, for the VHS CDC, presented to NACO - Qualitative research on quality of family planning services for Jhpiego, India - Coordinator, gap analysis of the GOI Reproductive, Maternal, New-born, Child and Adolescent (RMNCH +A) Strategy - for SRHR Alliance - Project coordinator – Scoping study and strategy on youth for SOS Children’s village international in Cambodia and Sri Lanka - Project coordinator – Strategy for Community Development & livelihoods in Bap Tehsil, Jodhpur, Rajasthan - Team member, Midline assessment and documentation of the model on ‘Enhancing community engagement and demand generation for urban sanitation’, IDSJ and CFAR - Team member – study on youth volunteerism in India, supported by UNDP - Team member, State Strategy and Action plan for Child marriage in Rajasthan - Documentation of case studies on children affected by Child marriage - Team member, Evaluation of Meena Manch in Rajasthan - Project Management support – Skill development for young people in Kerala - Strategy development and technical documentation for skilling visually impaired persons across India, for SCORE Foundation - Team member, Baseline Research on Critical Appraisal Skills for Public Health Reporting and Communication for Routine |

| Period | Organization/ Title | Summary of activities performed relevant to the Assignment |
| --- | --- | --- |
|  |  | Susan Dell Foundation (MSDF), in association with Samagra Governance and Niti Aayog - Process Evaluation of the Adarsh Vidyalaya Yojna in Rajasthan for MSDF, presented to State Government Rajasthan - Evaluation of ABL Program in Gujarat, for Central Square Foundation (CSF), presented to Government of Gujarat - Evaluation of Early Childhood Education Programs in Gujarat and Karnataka, for CSF - Evaluation support for the Health Rise Program for Institute of Health Metrics and Evaluation - Baseline on MHM in 5 districts of UP, for the WSSCC, UNOPS - Assessment of PLHIV and ART linkage (PALS) software for VHS- CDC - Organizational assessment of State Health Resource Centers for NHSRC - Operational plan for strengthening of VHSNCs in UP, for World Vision - Consultation on the National Health Policy 2015, for National Health Systems Resource Centre (NHSRC) Other projects: - Assessment and documentation of processes for the development of a software for linkage of PLHIV and ART, for the VHS CDC, presented to NACO - Qualitative research on quality of family planning services for Jhpiego, India - Coordinator, gap analysis of the GOI Reproductive, Maternal, New-born, Child and Adolescent (RMNCH +A) Strategy - for SRHR Alliance - Project coordinator – Scoping study and strategy on youth for SOS Children’s village international in Cambodia and Sri Lanka - Project coordinator – Strategy for Community Development & livelihoods in Bap Tehsil, Jodhpur, Rajasthan - Team member, Midline assessment and documentation of the model on ‘Enhancing community engagement and demand generation for urban sanitation’, IDSJ and CFAR - Team member – study on youth volunteerism in India, supported by UNDP - Team member, State Strategy and Action plan for Child marriage in Rajasthan - Documentation of case studies on children affected by Child marriage - Team member, Evaluation of Meena Manch in Rajasthan - Project Management support – Skill development for young people in Kerala - Strategy development and technical documentation for skilling visually impaired persons across India, for SCORE Foundation - Team member, Baseline Research on Critical Appraisal Skills for Public Health Reporting and Communication for Routine |

Paper presentations and Publications:

- Vasudha Chakravarthy, 'Women at the center of the Covid-19 pandemic: Insights from rural contexts in India'; Demography India Vol. 49, Special Issue (2020), pp. 132-139; ISSN 0970-454X

- Flor LS, Wilson S, Bhatt P, et al; Community-based interventions for detection and management of diabetes and hypertension in underserved communities: a mixed-methods evaluation in Brazil, India, South Africa and the USA; BMJ Global Health 2020;5:e001959.

- Vasudha Chakravarthy, S. Rajagopal, Bhavya Joshi - Does Menstrual Hygiene Management in Urban Slums Need a Different Lens? Challenges Faced by Women and Girls in Jaipur and Delhi; Indian Journal of Gender Studies 26(1&2) 138–159, 2019

- S. Ramanathan, Vasudha Chakravarthy. Structure of opportunities for adolescents – Policies and Programs on adolescent health in India. Published in book – Empowering Adolescents, 2017

- S. Ramanathan, Vasudha Chakravarthy. Child Labor in Global Production Networks: Evidence from two Industries; presented at the National Conference on Rural Transformation in India: Issues, prospects and challenges, Institute of Development Studies, Jaipur; December 4-6, 2014

- Practical approaches to designing standards: The case of a district hospital information system in northern India; Murodillo Latifov, Arunima Mukherjee, Vasudha Chakravarthy, Sundeep Sahay

- (Proceedings of the 11th international conference on social implications of computers in developing countries, Kathmandu, Nepal, May 2011)

Paper publications in progress:

- Currently in the process of peer review and finalization – S. Ramanathan, Vasudha Chakravarthy. ASHA- the bearer of hopes for others but not herself! (To be published in Anveshi Research Centre for Women’s Studies, Hyderabad, volume on Re-visiting the Labour Question: Challenges for labour)

#### Language Skills:

| Language | Reading | Writing | Speaking |
| --- | --- | --- | --- |
| Hindi | Fluent | Fluent | Fluent |
| English | Fluent | Fluent | Fluent |
| Tamil | Proficient in conversing |  |  |

| Name | Dr Prachitha J |
| --- | --- |
| Proposed Position in the team | Technical Expert – Health Systems |

Education:

| College/university | Dates Attended | Degree(s)/Diploma(s) obtained |
| --- | --- | --- |
| Madras School of Economics | 2013 | Ph. D in Development Economics, (Health/Public Economics) |
| Pondicherry Central University, Pondicherry | 2003 | M. S. (Development Economics) |

Core Competencies:

- Overall Management & Monitoring of Research/Survey Projects

- Formulation of Research Design

- Developing Tools for Research and Evaluation Studies

- Data Analysis - Statistical and Econometric Analysis and Interpretation

- Documentation skills – Preparation of Reports, Case Studies & Documentary Films

#### Areas of Specialization:

- Public Economics / Public Finance

- Health Economics / Public Health

- Development Economics / Poverty and Development–related Socio-economic Issues

#### Years of Professional Experience: 12 years

Professional Experience:

| Period | Organization/ Title | Summary of activities performed |
| --- | --- | --- |
| July 2019 till date | Senior Consultant (Public Financial Management), Ernst & Young LLP, New Delhi | - Developing the Debt Procedures Manual - Reviewing cash and debt management systems in the States, gathering information on international methodologies/best practices for debt analysis, risk management and debt reporting for developing the Debt Procedures Manual for the Government of Uttarakhand as part of the World Bank-assisted Uttarakhand Public Financial Management Strengthening Project - Support to PMU, Haryana – State Budget and Finance Management (SB&FM) Office, Finance Department, Haryana Civil Secretariat - Coordinate with the team and State officials on analysis of State expenditures, revenues and borrowings and identify gaps in the system to help the government plan its expenditure and committed payments, preparing daily dashboards on the status of the same - Assist the Finance department in budget preparation exercise - Support the newly formed State Economic Forum in developing a strategy paper for accelerating the growth momentum in the state - Support to the PFM team in on-going projects - Engaged in extensive business development activities in areas of budgeting and PFM |

| Period | Organization/ Title | Summary of activities performed |
| --- | --- | --- |
| December 2017 to June 2019 | Manager (Research), TRIOs Development Support (P) Ltd., New Delhi | - Developing Research Proposals/Bids/Expression of Interests on issues related to Health, Nutrition, WASH, Education, Livelihood and Rural development sector surveys leading to about Rs. 1.2 crores of business to the organization - Holding client meetings/ interactions and making presentations on project progress - Management of Field implementation Projects for Clients - Conducting Evaluations of Completed and On-going Projects/Programs for Various Clients. Important evaluation studies undertaken include: - Needs Assessment and Impact Assessments of the CSR interventions of Vedanta Resources Plc (along with TARU Leading Edge) - Analysis and documentation of final report for the ‘WASH Program’ in schools in Rajasthan under Dettol Banega Swachh India Campaign for Reckitt Benckiser - Baseline, Mid-line and End- line Evaluations of Magic Bus Program in West, North and East for MagicBus India Foundation. - Documenting Case Studies and Drafting Study Reports for Various Projects |
| June 2017 to November 2017 | Assistant Professor, PES (People’s Education Society) University, Bangalore | - Deliver lectures in development economics and public economics - Develop proposals and manage and execute research projects - Fund-raising for projects and workshops |
| December 2016 to May 2017 | Consultant – Research, Centre for Study of Social Change and Development (CSSCD), Institute for Social and Economic Change (ISEC), Bangalore | - Attending Client meetings (Dept. of H&FW) and making presentations on project progress. - Monitoring the works of the project staff (team of 4) and overall management of the evaluation activities including field work - Gathering and analyzing secondary data - Field visits for gathering primary information and for case studies. - Preparation of the script and plan for documentary film. - Drafting of the evaluation report |
| November 2012 to November 2016 | Consultant – Health Economics and Finance, Karnataka State Health System Resource Centre (KSHSRC), | - Attended the progress and performance meetings and budget preparation meetings of the Department of H&FW representing KSHSRC as the technical support unit - Finance Management System - Advocated, Devised and Facilitated a budget tracking system in Chitradurga district of Karnataka (as a pilot) by creating a mechanism for line item- wise matching physical and financial achievements at the health facility and programme management levels using Google spreadsheets. |

| Period | Organization/ Title | Summary of activities performed |
| --- | --- | --- |
|  | Directorate of Health & Family Welfare, Bangalore | - Budget and Expenditure Analysis - Conducted regular quarterly and yearly analysis of NHM finance utilization of the State and districts and identified good and poor performing districts with respect to fund utilization. - Operational Gap Analysis in Implementation of Vajpayee Arogyashree Scheme, Suvarna Arogya Suraksha Trust (SAST) - Developing of Perspective Plan for Suvarna Arogya Suraksha Trust (SAST) - Development of DHAP - Advocated developing District Health Action Plan (DHAP) and Coordinated the DHAP in two districts – Mysore and Chamarajanagar - NUHM Budgeting - Assisted with the planning and budgeting of NUHM in the State - Been part of various research projects related to healthcare financing and planning including: - State budget analysis - Quality assurance survey of urban health facilities in Mysore district - District-wise monthly analysis and grading of the status of health facilities in Karnataka - Assistance in the star-rating of PHCs and CHCs as per the GoI norms - Workshop on Supportive supervision of State nodal officers and analysis of the supportive supervision checklists submitted by nodal officers |
| March 2015 to August 2015 | Senior Project Officer (Part- time), Department of Management Studies, Indian Institute of Technology (IIT), Madras | - Developing the analysis template and analysis of the data gathered - Extensive literature review of the theoretical framework - Drafting of the study report |
| September 2011 to October 2012 | Project Officer, Department of Management Studies, Indian Institute of Technology (IIT), Madras | - Overall project management and monitoring of the works of the project staff (team of 5). - Systematic search for articles through search engines, websites, and cross-references - Screening for the relevant articles and studies by assigning work to the team using EPPI reviewer - Assessment of the quality of the selected studies - Meta-regression analysis - Drafting of the study report |
| January to June 2006 | Programme Coordinator, partnered by Janaagraha and Akshara | - Contributed to the development of the framework for participatory budgeting in the BBMP schools in Bangalore - Assisted in preparation of the scoring scheme for rating the infrastructure and teaching in schools |

| Period | Organization/ Title | Summary of activities performed |
| --- | --- | --- |
|  | Foundation, Bangalore |  |
| March 2004 to December 2005 | Research Assistant with Prof. R S Deshpande at Institute for Social and Economic Change (ISEC), Nagarbhavi, Bangalore | - Assisted with collection of secondary data and literature for various projects relating to agriculture and rural development. - Analysis of secondary and primary data for various projects at the Agriculture and Rural Development Unit of ISEC - Assisted with drafting of research reports of the Unit. |

Paper presentations and Publications:

Journal Publications

- “India in Pursuit of Millennium Development Goals 4 and 5: Were the Targets Really Feasible?” co-authored with Dr. Akshay Dhume and Dr. Subramanian published in Journal of Developing Societies, Special Issue, 35(1), March 2019.

- “Public Expenditure Policy Interaction among the State Governments in India” co-authored with Prof. K R Shanmugam, CDS@PES Working Paper - 002, Centre for Development Studies, PES University, Bangalore, May 2017.

- “Impact of Private Sector Participation on Access and Quality of Services: Systematic Review of Evidence from the Electricity, Telecommunications and Water Supply Sectors” co-authored with Prof. Ashwin Mahalingam, Prof. Akash Deep and Prof. A Thillairajan published in Journal of Development Effectiveness, September 2014.

- “Efficiency of Raising Health Outcomes in Indian States”, co-authored with Prof. K R Shanmugam, published in International Journal of Applied Economics and Econometrics, 2014, Vol. 22 (1), pp 89-108.

- “Entangled at the Crossroads: Growth and Employment in Indian Agriculture”, co-authored with Prof. R S Deshpande, published in Agricultural Situation in India, August 2004.

- “Causal Nexus between Fiscal Deficits and Macro-economic Variables in Indian States”, with Prof K Sham Bhat in K Sham Bhat (ed.) Issues in Financial Development, New Delhi: Serial Publications, 2004

Report Publications

- “WTO and Agricultural Policy in Karnataka” (Co-author) published as ISEC Research Report, March 2005.

- “Building Up of An Efficient Marketing System to Obviate the Need for Large Scale State Intervention in Karnataka”, Co-author with Prof. R S Deshpande, published as ISEC Research Report, June 2004.

Papers Presented in Seminars/Conferences

- “Health Expenditure of State Governments in India: Determinants and Needs” – Presented at the Second National Conference of Health Economics Association of India (HEAI) on “Strengthening Health Systems in India: What Works and What Lies Ahead?” held at SRM University from 29-31st May, 2013

- “Public Expenditure Policy Interaction among State Governments in India” – Co-authored with Dr. K R Shanmugam – Presented at the 44th Annual Conference of The Indian Econometric Society (TIES) held at the University of Hyderabad from 3-5th January 2008.

- “Intellectual Property Rights: A Travelogue from Techno-economy to Political Economy” – co- authored with Prof. R S Deshpande - Presented at the Conference on “IPRs: Different Facets” held at Mysore (Sept. 26-27, 2005)

#### Language Skills:

| Language | Reading | Writing | Speaking |
| --- | --- | --- | --- |
| Hindi | Fluent | Fluent | Fluent |
| English | Fluent | Fluent | Fluent |
| Tamil | Fluent | Fluent | Fluent |
| Kannada | Fluent | Fluent | Fluent |
| Malayalam | Fluent | Fluent | Fluent |

| Name: | Riza Mahanta |
| --- | --- |
| Proposed position in the team | Project Manager |

Education:

| College/university | Dates Attended | Degree(s)/Diploma(s) obtained |
| --- | --- | --- |
| Azim Premji University | 2016 | M.A. Development |
| Delhi University | 2013 | B.A. (Honours.) – Sociology |

Years of Professional Experience: 4 years

Professional Experience:

| Period | Organisation/ Title | Summary of activities performed |
| --- | --- | --- |
| August 2017 - Present | Project Coordinator, Development Solutions | Coordinated multiple projects including: - Rapid assessment on impact of COVID-19 on availability and access to health and nutrition services for children, adolescents and women, supported by Population Foundation of India - Assessment of the Programme for ‘Children in Contact with Railway Stations’ (CCRS) for Azim Premji Philanthropic Initiatives - Midline and end line assessment of the Rajasthan Hotspot Project on Children in Labor, Freedom Fund - Evaluation of ‘Boys Stand Up’ which targets adolescent boys in Rajasthan to influence patriarchal gender norms, centre consensual sex and improve sexual health behaviours, CIFF - Assessment & Validation of Impact under the Systemic School Education Transformation Programs in 4 States for MSDF and Samagra - Third party audit of the ‘Facilitating Learning Action Groups’ (FLAG) program which aims to reduce neonatal mortality by up to 33% in Jharkhand, CIFF - Study on Acceptability of menstrual cups as a sustainable, cost-effective, and non-polluting menstrual hygiene solution for menstrual health in India in collaboration with University of Liverpool, UK - Partnership to foster an enabling environment on Menstrual Hygiene Management programs in India- review of MHM IEC materials in India for UNICEF - Baseline study on menstrual hygiene management in Uttar Pradesh, WSSCC - Household survey, 1000 households in Bap Tehsil, Jodhpur - Baseline assessment of the Rajasthan Hotspot Project on Children in Labor, Freedom Fund - Project management and consulting for ILFS in Jodhpur - Development of M&E framework for the Microsoft CSR |
| June 2016 – July 2017 | Aajeevika Bureau | - Conducted an intensive study on type of activities conducted and level of women empowerment achieved under their Family Empowerment Program |
| Period | Organisation/ Title | Summary of activities performed |
|  |  | - Form groups of adolescent girl workers and impart life skill sessions. - Develop material for activities and sessions conducted under Family Empowerment Program (FEP). - Collect and analyse data of the families touched by the organisation and identify the vulnerable pockets/families in the area and develop strategies to connect and facilitate them on a priority basis. - Understand all the welfare schemes provided by the government and link the beneficiaries with those schemes. - Handle all FEP related data and reports, including writing the bi-monthly - Report of the unit and all the activities conducted under it. - Taking lead in their research project on Single Women of rural Rajasthan. |
| November - December 2015 | Researcher, Prayas Centre for Labour Research and Action | - Conducted an intensive study on the living and working conditions of construction workers. - The research was to look in to how the construction workers, who are mainly migrants, get the work and what are their living conditions. I also assessed their socio- economic and health conditions. |
| May- June 2015 | Field Researcher, Central Himalayan Environment Association (CHEA) | - Conducted a cross check study assess the achievements/impact of CHEA’s “Bamboo Livelihood” interventions in Uttarakhand. - The team designed a questionnaire keeping in mind the work being done by CHEA for the betterment of the bamboo workers, the types of product they make, and the socio-economic aspect of the project. |
| May 2012 | Volunteer, Satark Nagrik Sangathan | - On-Field research work, and spread awareness regarding RTI |

Language Skills:

| Language | Reading |  | Writing | Speaking |  |
| --- | --- | --- | --- | --- | --- |
| English | Fluent |  | Fluent | Fluent |  |
| Hindi | Fluent |  | Fluent | Fluent |  |
| Assamese | Fluent |  | Fluent | Fluent |  |
| Name |  | R. Vinaygam |  |  |
| Proposed position in the team |  | M&E Manager |  |  |

Education:

| College/university | Dates Attended | Degree(s)/Diploma(s) obtained |
| --- | --- | --- |
| Azim Premji University, Bangalore | 2016 | Master’s in development (Public Policy) |
| Ram Lal Anand College, Delhi University | 2012 | Bachelor of Commerce |

Years of Professional Experience: 4 years

Professional Experience:

| Period | Organization/ Title | Summary of activities performed |
| --- | --- | --- |
| June 2018 till present | Development Solutions, Manager- M&E | M&E coordinator and data analyst for multiple projects including: - Rapid Assessment – Impact of COVID-19 on availability and access to health and nutrition services for women, children and adolescents supported by Population Foundation of India - Assessment of the Programme for ‘Children in Contact with Railway Stations’ (CCRS) for Azim Premji Philanthropic Initiatives - End-line study to assess the impact of the project Samvaad on the knowledge, skills and attitudes of SSK & RKSK counsellors in Madhya Pradesh for Tata Institute of Social Sciences (TISS) - Feasibility assessment of livelihood situation and opportunities in four states, for Save the Children - Research study on DIKSHA, a national education technology program of the Ministry of Human Resource Development (MHRD) - Evaluation of the School Transition Program in Karnataka and Gujarat, Central Square Foundation - Impact and process assessment of Adarsh Vidyalaya Yojana implemented by Government of Rajasthan for MSDF - Online survey with young persons to understand the impact of COVID-19 on the education - Evaluation of MTV Nishedh and Girl Effect Chaa Jaa supported by CIFF - Evaluation of Boys Stand Up Project supported by CIFF - Evaluation of the HealthRise Program in Shimla and Udaipur, Institute for Health Metrics and Evaluation - FLAG program to reduce neonatal and maternal deaths in Jharkhand supported by CIFF - Evaluation of a group of pilot interventions – ‘Matrix of Change ’Matrix of Change’ Project, CIFF - Baseline assessment of SHOPS Plus Project, Abt Associates |
| Period | Organization/ Title | Summary of activities performed |
|  |  | - Study on Productivity & Working Conditions in Natural Stone Mining Industry Supply Chain, ILO - Involved with project conceptualization and proposal development, providing inputs on research design and sampling - Support with overall data management and data analysis in the organization |
| September 2017 – January 2018 | Researcher (Process evaluation), TATA Institute of Social Science | - Process evaluation of project ‘Zero Investment Innovation for Education Initiatives’ (ZIIEI), Sri Aurobindo Society - Designing and implementation of data collection tools. - Data collection via In-depth interview, FGDs & survey. - Coordination with stakeholders for data collection schedule. - Documentation and transcription of data - Report writing and data presentation |
| April 2017 – September 2017 | Consultant – Research and evaluation, Population Council | - Support impact evaluation studies covering various districts of Bihar and UP - Writing proposals for evaluation study, preparing data sharing agreement and calls/RFPs for consultants. - Contribute in preparation of impact evaluation and process evaluation. - Technical input data collection tool. Converting the tool in CAPI - Data cleaning, documentation, secondary research and desk review |
| October 2016 – March 2017 | Consultant – Research (Evidence Gap Map), International Initiative for Impact Evaluation (3IE) | - Collection and compilation of existing data on studied theme. - Review, screening and coding of evaluation studies. - Maintain detailed documentation of the review process - Proposal writing and budgeting for producing EGMs in various domains. |
| July 2013 – December 2013 | Project Coordinator, Hope Foundation | - Project planning, monitoring and implementation. - Report preparation. - Liaise with donors for planning & external teams for project implementation. - Documentation & maintenance of project data. - Supervising surveys. |

Language Skills:

| Language | Reading | Writing | Speaking |
| --- | --- | --- | --- |
| Hindi | Fluent | Fluent | Fluent |
| English | Fluent | Fluent | Fluent |

| Name | Varun Chakravarthy |
| --- | --- |
| Proposed position in the team | Data Analytics Expert |

Education:

| College/university | Year of Completion | Degree(s)/Diploma(s) obtained |
| --- | --- | --- |
| University of Bristol, UK | 2013 | M.Sc. Economics and Public Policy |
| University of Delhi | 2012 | B.A. in Economics |

Professional Experience:

| Period | Title/ Organization | Summary of Activities Performed |
| --- | --- | --- |
| October 2018 to present | Director, Sociometrik Infer Pvt. Ltd. | - Team lead – data partner, engagement with Niti Aayog for the National Data Analytics portal - Team lead – analytical support to Delhi and Indore war rooms for Covid-19 - Develop one square kilometer Covid-19 risk susceptibility maps, for ten major Indian cities published in the Mint - Team lead - Flood detection and damage assessment using remote sensing and quantitative methods, for Government of Assam - Team lead – Analytics – effect of climate change on human development indicators, UNDP - Team lead – mapping access to education for vulnerable populations using location intelligence, for Dr. Ambedkar International Center (DAIC) - Consultant – Crop classification and acreage detection, for department of land revenues, Government of Madhya Pradesh - Team lead – roof classification and demand pocket estimation using machine learning and econometric modelling, for Accenture - M&E lead – evaluation of the ‘matrix of change’ intervention – development of M&E design, data analysis based on primary sample surveys, secondary data analysis, and use of geospatial analysis and location intelligence to assess differential impact - Co-Team lead - Assessment & Validation of Impact under the Systemic School Education Transformation Programs, Micheal and Susan Dell Foundation (MSDF), presented to the Niti Aayog - Lead analyst – baseline assessment of the Sustaining Health Outcomes through the Private Sector (SHOPS) Plus project, Abt Associates |
| June 2015- October 2018 | Manager, IDinsight | - Setup a data infrastructure in 27 districts under the ‘aspirational districts program’ of the Niti Aayog/GOI to facilitate high frequency monitoring of Socio-Economic Indicators - Led a 2-year experimental design impact evaluation; and process monitoring to assess the impact of teacher motivation on student learning, for STIR Education - Baseline assessment – rural livelihood scheme, Society for Elimination of Rural Poverty (SER), Government of Andhra Pradesh |

| Period | Title/ Organization | Summary of Activities Performed |
| --- | --- | --- |
| 2014- 2015 | Indicus Analytics | - Development of socio-demographic and consumer segmentation products – using a combination of geospatial analytics and secondary data analysis - Worked on revised poverty estimates for the erstwhile planning commission - Identification of India’s most affluent pin codes, using geospatial analytics and secondary data, published in the Livemint |

Skilled At:

- Geospatial Analytics, STATA, R

#### Language Skills:

| Language | Reading | Writing | Speaking |
| --- | --- | --- | --- |
| Hindi | Excellent | Excellent | Excellent |
| English | Excellent | Excellent | Excellent |

Budget

The total budget for proposed engagement will be USD 29,940 inclusive of all applicable taxes.

Bank Account Details

| Name of the Beneficiary | : | Development Solutions Inc |
| --- | --- | --- |
| Bank Name | : | HDFC Bank Ltd |
| Bank Address | : | A – 9, Ring Road, Lajpat Nagar IV, New Delhi -110024, India |
| Account Number | : | 50200005595194 |
| IFSC Code | : | HDFC0000294 |
| Swift Code | : | HDFCINBB |

Remuneration

The entire fee/compensation, not exceeding USD 29,940 inclusive of all applicable taxes would be paid in below tranches to the account mentioned above held by Development Solutions Inc.

Deliverables and Payment

| Activity/Deliverable | Percentage of Payment |
| --- | --- |
| Submission of Inception Report | 30% |
| Progress Report (Mid Term Update) | 20% |
| Submission of Research Data | 20% |
| Submission of Final Report | 20% |
| Submission of Policy Brief | 10% |

Term of Contract

This contract period is from November 16, 2020 to May 15, 2021. Development Solutions Inc will be engaged under the agreement from the date of signing the contract till the date of closure as mentioned above. The contract will be considered closed when the deliverable is received, and final report is submitted.